## Starbucks_updated Roadmap
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Starbucks Roadmap to Success
Enter Company Name in cell B2. | Company Name | STARBUCKS
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead | AZMINA SAYYED |  | 2024-03-05
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Starbucks Roadmap to Success | Display Week: |  | 1 |  |  | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-03-04 to 2024-08-25
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2024-03-04 to 2024-08-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | System (Sales) - Steps to take while Introducing a new product.
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Introduce & Offer the new product to various consumer segments | Marketing & Sales dept. heads | 0% | 2024-03-05 | 2024-05-14 | 71
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Collect preliminary data related customer reviews. | Marketing Analysts | 0% | 2024-05-14 | 2024-06-28 | 46
| Collect seconday data after a specifc time-period from the same customers | Marketing Analysts | 0% | 2024-06-28 | 2024-07-28 | 31
| Analyze data collected to draw actionable insights | Marketing Data Analysts | 0% | 2024-07-28 | 2024-09-26 | 61
| Introduce the product to the market | Marketing & Sales dept. heads |  | 2024-09-27 | 2024-10-17 | 21
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | People - Restructuring Higher Management for Data & Analytics Team
| Identify the need for a senior (Chief Data Officer - CDO) position for the Data & Analytics team | Organization Leaders | 0% | 2024-05-15 | 2024-07-14 | 61
| Assess the cost for promoting the current Senior VP to a CDO and for hiring a replacement for the Senior VP | Senior Financial Analysts & Higher Management | 0% | 2024-07-20 | 2024-09-18 | 61
| If the budget for the company allows it, create a posting for the Senior VP | Senior Hr Analyst | 0% | 2024-09-18 | 2024-10-18 | 31
| Promote the Senior VP to a CDO | HR department & Leaders | 0% | 2024-11-01 | 2025-01-30 | 91
| Interview & Hire the Senior VP | HR & CDO | 0% | 2024-11-01 | 2024-12-31 | 61
Sample phase title block | Culture - Improving Employee Satisfaction
| Create a Employee Satisfaction Survey | Associate HR | 0% | 2024-03-07 | 2024-03-17 | 11
| Send out a survey to the employees | HR Analyst | 0% | 2024-03-22 | 2024-04-21 | 31
| Gather survey data & transform into a format ready for analysis | HR Analyst | 0% | 2024-04-06 | 2024-04-26 | 21
| Analyze data collected to draw actionable insights | Business/Data Analyst | 0% | 2024-04-27 | 2024-05-27 | 31
| Review Insights and discuss with Higher Management | Supervisor/Manager | 0% | 2024-05-27 | 2024-05-31 | 5
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Including various geographical regions

## Summary
Summary of risks , assumptions and quick wins
Category | Systems | People | Culture
| This specific category would be applicable only when there is a new product is to be launched in the market. Timelines on this may be delayed or tasks would take longer if the product is tested in different geographical regions. | Starbucks currently does not have an operating Chief Data Officer. This new role would help in overseeing strategic initiatives for the organization's technological advancement. | This category focuses on employee enrichment which would result in a low turnover and higher employee engagement and satisfaction.
Assumptions | This task assumes the new product has been idealized and manufactured and ready to be introduced. | N/A | This Category should be priortized since there is no cost associated with it directly but would be valuable to the organization
Risks | The risks for the 1st task in this category is related to specifically to find customers willing to try the new products. There might be a delayed timeline if customers approached deny the trial | Task 1 in this category has a potential risk of being delayed if there is no buy-in from the higher management or if the budget does not accommodate for the role | The only risk for this category would be if employees deny participation in the survey. This can be overcomed by keeping the surveys anonymous as well as the responses anonymous so employees can have a trust factor that they can rely on the confidentiality and respond with genuine feedback.
| The risks for the 3rd task in this category is the customers availability / willingness to provide feedback after the trial. Delay in responses might delay the further steps related to collection & analyzing of data. | Timelines might be delayed if the search for appropriate candidate takes longer than anticipated.
Quick Wins | If the trial with customers is successful , Starbucks can use the insights from the trial data to call out the customers(if consent is received) and make their ads more connectable with audiences, increasing trust and sales on the new product. | Quick wins for this category would be delegation of responsibilities to focus more on future initiatives as technology advancements roll out so that company continues to be at level 5 of the Analytical maturity model. | Using the data gathered from the employees to analyze what the employees value as well what changes would they like to see. A quick win for an organization would be implementing on the suggestions that received a majority of votes which would avoid the chances of union strikes that disrupt the company's reputation.

## Costs
Costs | 2024 | 2025
Systems
Sampling of products | 15000 | 0
Culture
Survey | 1000 | 0
People
CDO Salary | 100000 | 180000 | 84
Senior VP salary | 10000 | 140000
Annual Total | 126000 | 320000 | 10
Total Investment |  | 446000

## Old_roadmap (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Starbucks Roadmap to Success
Enter Company Name in cell B2. | Company Name | STARBUCKS
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead (Your Name) | AZMINA SAYYED |  | 2024-03-05
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-03-04 to 2024-08-25
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2024-03-04 to 2024-08-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | System (Sales) - Steps to take while Introducing a new product.
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Introduce & Offer the new product to various consumer segments | Marketing & Sales dept. heads | 20% | 2024-03-05 | 2024-03-11 | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Collect preliminary data related customer reviews. | Marketing Analysts | 10% | 2024-03-11 | 2024-03-23 | 13
| Collect seconday data after a specifc time-period from the same customers | Marketing Analysts | 5% | 2024-03-23 | 2024-03-30 | 8
| Analyze data collected to draw actionable insights | Marketing Data Analysts | 0% | 2024-03-30 | 2024-04-13 | 15
| Introduce the product to the market | Marketing & Sales dept. heads |  | 2024-04-14 | 2024-04-16 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | People - Restructuring Higher Management for Data & Analytics Team
| Identify the need for a senior (Chief Data Officer - CDO) position for the Data & Analytics team | Organization Leaders | 0% | 2024-05-15 | 2024-05-29 | 15
| Assess the cost for promoting the current Senior VP to a CDO and for hiring a replacement for the Senior VP | Senior Financial Analysts & Higher Management | 0% | 2024-06-04 | 2024-06-14 | 11
| If the budget for the company allows it, create a posting for the Senior VP | Senior Hr Analyst | 0% | 2024-06-14 | 2024-06-17 | 4
| Promote the Senior VP to a CDO | HR department & Leaders | 0% | 2024-07-01 | 2024-07-31 | 31
| Interview & Hire the Senior VP | HR & CDO | 0% | 2024-07-01 | 2024-07-04 | 4
Sample phase title block | Culture - Improving Employee Satisfaction
| Create a Employee Satisfaction Survey | Associate HR | 0% | 2024-03-07 | 2024-03-12 | 6
| Send out a survey to the employees | HR Analyst | 0% | 2024-03-13 | 2024-03-17 | 5
| Gather survey data & transform into a format ready for analysis | HR Analyst | 0% | 2024-03-18 | 2024-03-23 | 6
| Analyze data collected to draw actionable insights | Business/Data Analyst | 0% | 2024-03-24 | 2024-03-28 | 5
| Review Insights and discuss with Higher Management | Supervisor/Manager | 0% | 2024-03-18 | 2024-03-22 | 5
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Including various geographical regions